## Sheet1
Task | Assigned to | Assignation Date | Actual Start Date | Duedate | Estimated working hours | Status
search about timers in avr |  | 29/1 |  | 2020-02-05 | 3h
write a working code of blinking led with timer in avr |  | 29/1 |  | 2020-02-05 | 5h
search about PWM |  | 29/1 |  | 2020-02-05 | 2h
move 1 servo with avr using PWM |  | 29/1 |  | 2020-02-05 | 5h
move 5 servos with avr using PWM |  |  |  |  | 2h
apply the PWM code in moving fingers of a robotic arm |  |  |  |  | 5h
connect the kinect and setup tools | Areej | 29/1 |  | 2020-02-03 | 1h
connect the kinect and setup tools | Refaat | 29/1 |  | 2020-02-03 | 1h
connect the kinect and setup tools | Marcelle | 29/1 |  | 2020-02-03 | 1h
connect the kinect and setup tools | Mina | 29/1 |  | 2020-02-03 | 1h
show skeletal data on matlab from kinect |  |  |  |  | 5h
send data from matlab to arduino |  |  |  |  | 5h
moving fingers of a robotic arm with signal from kenict with arduino
(Milestone 1 Reached in 6/2/2020) move the servos with signal from kenict