## Sheet1
Task | Assigned to | Assignation Date | Actual Start Date | Duedate | Estimated working hours | Status
search about timers in avr | Refaat | 30/1 |  | 2020-02-05 | 3h | Asseigned
write a working code of blinking led with timer in avr | Refaat,areej | 30/1 |  | 2020-02-05 | 5h | Asseigned
search about PWM | Marcelle | 30/1 |  | 2020-02-05 | 2h | Asseigned
move 1 servo with avr using PWM | Mina | 30/1 |  | 2020-02-05 | 5h | Asseigned
move 5 servos with avr using PWM | all team | 30/1 |  | 2020-02-05 | 2h | Asseigned
apply the PWM code in moving fingers of a robotic arm | all team | 30/1 |  | 2020-02-05 | 5h | Asseigned
connect the kinect and setup tools | sara | 28/1 | 28/1 | 2020-02-03 | 1h | done
connect the kinect and setup tools | Areej | 29/1 |  | 2020-02-03 | 1h | Asseigned
connect the kinect and setup tools | Refaat | 29/1 |  | 2020-02-03 | 1h | Asseigned
connect the kinect and setup tools | Marcelle | 29/1 |  | 2020-02-03 | 1h | Asseigned
connect the kinect and setup tools | Mina | 29/1 |  | 2020-02-03 | 1h | Asseigned
show skeletal data on matlab from kinect | sara,areej,refaat | 29/1 |  | 2020-02-05 | 5h | In progress
send data from matlab to arduino | mina | 30/1 |  | 2020-02-05 | 5h | Asseigned
moving fingers of a robotic arm with signal from kenict with arduino | all team | 30/1 |  | 2020-02-05 | 2h | Asseigned
(Milestone 1 will be reached in 6/2/2020) move the servos with signal from kenict